## project_risks
risk_id | category | risk_challenge | impact | mitigation_strategy | last_updated | status
R01 | Data Quality & Availability | Incomplete or unstructured data | Poor model performance and inaccurate outcomes | Perform early data audits and implement robust data governance | 2026-09-05 | Open
R02 | Integration Issues | Difficulty integrating AI with legacy systems | Delays in deployment and operational disruptions | Plan integration roadmap and use APIs/middleware | 2026-09-05 | Open
R03 | Talent & Skills Gap | Lack of internal AI/ML expertise | Overreliance on external vendors and slow progress | Provide staff training and hire specialized talent | 2026-09-05 | Open
R04 | Change Resistance | Employees resist adopting AI-driven workflows | Low adoption and reduced ROI | Strong change management and early engagement | 2026-09-05 | Open
R05 | Ethical & Legal Concerns | Risks of biased models or data privacy violations | Legal repercussions and reputational damage | Involve legal early and implement fairness checks | 2026-09-05 | Open
R06 | Cost Overruns | Underestimation of AI development costs | Budget constraints and project delays | Set realistic budget and build in contingency funds | 2026-09-05 | Open
R07 | Unrealistic Expectations | Stakeholders expect immediate ROI | Disillusionment and loss of support | Align expectations and show quick wins | 2026-09-05 | Open
R08 | Model Performance Drift | AI models lose accuracy over time | Incorrect decisions and trust erosion | Regular retraining cycles and monitoring dashboards | 2026-09-05 | Open
R09 | Security Vulnerabilities | AI models targeted by adversarial attacks | Data breaches and operational risks | Adopt AI security best practices and penetration testing | 2026-09-05 | Open
R10 | Resource Bottleneck | Loss of continuity in data analysis and pipeline development due to Priya Nair's departure. | Delays in project timelines and potential quality issues in deliverables. | Reassign tasks to other team members and ensure knowledge transfer before her departure. | 2026-09-21 | Open
R11 | Milestone Delays | Potential delays in achieving milestones related to data pipelines and analysis. | Impact on project timelines and deliverables for Sprint 2 and Sprint 4. | Identify and onboard a replacement or redistribute tasks among existing team members. | 2026-09-21 | Open
R12 | Resource Bottleneck | Loss of continuity in project tasks due to Arjun Mehta's departure. | Delays in project timelines and potential quality issues in deliverables. | Reassign tasks to other team members and ensure knowledge transfer before his departure. | 2026-09-21 | Open