## task_board
task_id | task_name | status | assignee | priority | sprint | start_date | due_date | labels | description
T001 | Define project scope and objectives | Done | Arjun Mehta | High | Sprint 1 | 31-08-2026 | 2026-08-09 | Planning | Document project scope, goals, and success criteria for AI adoption
T002 | Form cross-functional task force | Done | Sarah Lin | High | Sprint 1 | 31-08-2026 | 2026-08-09 | Planning | Identify and onboard team members from data science, IT, and business units
T003 | Initial stakeholder alignment meeting | Done | Arjun Mehta | High | Sprint 1 | 31-08-2026 | 2026-11-09 | Planning | Present project charter and get sign-off from leadership
T004 | Audit existing data infrastructure | Done | Priya Nair | High | Sprint 2 | 31-08-2026 | 2026-11-09 | Analysis | Assess current databases, data pipelines, and data quality
T005 | Map current logistics workflows | In Progress | James Wong | Medium | Sprint 2 | 2026-11-09 | 19-09-2026 | Analysis | Document end-to-end processes for demand forecasting, routing, and inventory
T006 | Identify data gaps and quality issues | To Do | Priya Nair | High | Sprint 2 | 14-09-2026 | 22-09-2026 | Analysis | Gap analysis report comparing available data vs requirements for AI models
T007 | Shortlist AI use cases | To Do | Arjun Mehta | High | Sprint 3 | 28-09-2026 | 29-09-2026 | Use Cases | Evaluate and prioritize: demand forecasting, route optimization, inventory mgmt, customer support
T025 | Legal review of data usage | To Do | Sarah Lin | High | Sprint 3 | 28-09-2026 | 29-09-2026 | Compliance | Review data privacy compliance for using customer delivery data in ML models
T008 | Define success criteria for each use case | To Do | Sarah Lin | High | Sprint 3 | 28-09-2026 | 2026-03-10 | Use Cases | Set measurable KPIs: 15% reduction in delivery delays, 10% cost reduction
T009 | Vendor evaluation for ML platform | To Do | James Wong | Medium | Sprint 3 | 28-09-2026 | 2026-06-10 | Use Cases | Compare cloud ML platforms (AWS SageMaker, Azure ML, GCP Vertex AI)
T010 | Collect historical demand data | To Do | Priya Nair | High | Sprint 4 | 2026-12-10 | 13-10-2026 | Data Prep | Extract 2 years of demand data from ERP system
T011 | Data cleaning and preprocessing pipeline | To Do | Priya Nair | High | Sprint 4 | 2026-12-10 | 20-10-2026 | Data Prep | Build automated pipeline for data cleaning, normalization, feature engineering
T012 | Design demand forecasting model | To Do | Ravi Kumar | High | Sprint 4 | 2026-12-10 | 20-10-2026 | Model Dev | Select algorithm (LSTM, Prophet, XGBoost), define input features
T013 | Design route optimization model | To Do | Ravi Kumar | Medium | Sprint 5 | 26-10-2026 | 27-10-2026 | Model Dev | Graph-based optimization with constraints (time windows, vehicle capacity)
T024 | Security review of AI infrastructure | Blocked | James Wong | High | Sprint 5 | 26-10-2026 | 27-10-2026 | Security | Penetration testing and vulnerability assessment - BLOCKED: waiting for security team availability
T014 | Build model training pipeline | To Do | Ravi Kumar | High | Sprint 5 | 26-10-2026 | 2026-03-11 | Model Dev | Automated training, validation, and model versioning
T015 | Deploy demand model to test environment | To Do | James Wong | High | Sprint 6 | 2026-09-11 | 2026-10-11 | Pilot | Deploy to staging, set up monitoring, define test scenarios
T016 | Run pilot with logistics team | To Do | Arjun Mehta | High | Sprint 6 | 2026-09-11 | 17-11-2026 | Pilot | 2-week pilot with 3 logistics coordinators using demand forecasting predictions
T017 | Collect pilot feedback and metrics | To Do | Sarah Lin | High | Sprint 7 | 23-11-2026 | 24-11-2026 | Evaluation | Survey users, measure prediction accuracy, compare with manual forecasts
T018 | Iterate on model based on feedback | To Do | Ravi Kumar | Medium | Sprint 7 | 23-11-2026 | 2026-01-12 | Evaluation | Adjust features, retrain model, validate improvements
T019 | Prepare production deployment plan | To Do | James Wong | High | Sprint 8 | 2026-07-12 | 2026-08-12 | Deployment | Infrastructure scaling, rollback plan, monitoring setup
T020 | Staff training program | To Do | Sarah Lin | Medium | Sprint 8 | 2026-07-12 | 15-12-2026 | Deployment | Train 25 logistics staff on using AI-powered forecasting dashboard
T021 | Full production rollout | To Do | Arjun Mehta | High | Sprint 9 | 21-12-2026 | 22-12-2026 | Deployment | Go-live for demand forecasting across all 3 distribution centers
T022 | Set up continuous monitoring | To Do | Priya Nair | High | Sprint 9 | 21-12-2026 | 29-12-2026 | Monitoring | Model performance dashboards, drift detection alerts, retraining triggers
T023 | Project closure report | To Do | Arjun Mehta | Medium | Sprint 10 | 2027-04-01 | 2027-05-01 | Monitoring | Final report: outcomes vs targets, lessons learned, recommendations for Phase 2
T026 | Complete staff training rollout (remaining sites) | To Do | Sarah Lin | Medium | Sprint 11 | 18-01-2027 | 25-01-2027 | Deployment | Extend AI dashboard training to remaining 2 distribution centers
T027 | Full production rollout sign-off (all distribution centers) | To Do | Arjun Mehta | High | Sprint 11 | 18-01-2027 | 25-01-2027 | Deployment | Formal go-live confirmation across all 3 distribution centers
T028 | Monitor model performance post-launch | To Do | Priya Nair | High | Sprint 12 | 2027-01-02 | 2027-08-02 | Monitoring | Track live prediction accuracy and drift against baseline for 2 weeks post go-live
T029 | Conduct final project review workshop | To Do | Arjun Mehta | Medium | Sprint 12 | 2027-01-02 | 2027-08-02 | Monitoring | Stakeholder workshop: outcomes vs targets, lessons learned
T030 | Publish recommendations for Phase 2 scaling | To Do | Arjun Mehta | Medium | Sprint 12 | 2027-01-02 | 14-02-2027 | Monitoring | Final recommendations report for scaling AI adoption beyond pilot departments