## project_timeline
milestone_id | phase_number | phase_name | milestone_name | planned_start_date | planned_end_date | status | owner | dependency_task_ids
M01 | 1 | Project Initiation | Team structure finalized | 31-08-2026 | 13-09-2026 | Done | Arjun Mehta | T002
M02 | 1 | Project Initiation | Project charter signed off | 31-08-2026 | 13-09-2026 | Done | Arjun Mehta | T001;T003
M03 | 2 | Current State Analysis | Current systems audit report | 14-09-2026 | 27-09-2026 | Done | Priya Nair | T004
M04 | 2 | Current State Analysis | Gap analysis report | 14-09-2026 | 27-09-2026 | In Progress | Priya Nair | T005;T006
M05 | 3 | Use Case Selection | Final prioritized use case list with success criteria | 28-09-2026 | 2026-11-10 | In Progress | Arjun Mehta | T007;T008;T009
M06 | 4 | Pilot Design | Data pipelines established | 2026-12-10 | 2026-08-11 | Not Started | Priya Nair | T010;T011
M07 | 4 | Pilot Design | Working prototype models | 2026-12-10 | 2026-08-11 | Not Started | Ravi Kumar | T012;T013;T014
M08 | 5 | Pilot Implementation | Pilot results report | 2026-09-11 | 2026-06-12 | Not Started | James Wong | T015;T016
M09 | 5 | Pilot Implementation | User feedback and performance metrics | 2026-09-11 | 2026-06-12 | Not Started | Sarah Lin | T017
M10 | 6 | Evaluation & Iteration | Updated models and process refinements | 2026-07-12 | 20-12-2026 | Not Started | Ravi Kumar | T018
M11 | 7 | Full Deployment | Full production rollout | 21-12-2026 | 31-01-2027 | Not Started | Arjun Mehta | T019;T021;T027
M12 | 7 | Full Deployment | Training sessions completed | 21-12-2026 | 31-01-2027 | Not Started | Sarah Lin | T020;T026
M13 | 8 | Monitoring & Review | Project closure report | 2027-01-02 | 14-02-2027 | Not Started | Arjun Mehta | T023;T029
M14 | 8 | Monitoring & Review | Recommendations for future scaling | 2027-01-02 | 14-02-2027 | Not Started | Arjun Mehta | T022;T028;T030